## Swimming NSW Estimate
Swimming NSW — Website Redevelopment
Project Estimate — 2026 Rates (ex GST)
Block | Task / Deliverable | Role | Hrs | Rate ($/hr) | Amount (ex GST)
Block 1: Project Setup & Blueprint Strategy |  |  |  |  | 7380
| Project setup, brief documents, 'Let's Get Started' questionnaire | PM | 10 | 210 | 2100
| Kickoff meeting (client + Mettro team) | PM | 2 | 210 | 420
| Blueprint Strategy document (CPT field definitions, component map, sitemap review, content architecture) | Strategy | 18 | 270 | 4860
Block 2: Website Design — Artwork Adaptation | Working from client-supplied JPEG artworks. Mettro will translate to responsive, production-ready artwork. Where source files are unavailable, AI image generation will be used where possible (results may require manual refinement). |  |  |  | 9870
| Homepage + mega menu design | Design | 10 | 210 | 2100
| Interior / standard content page template | Design | 5 | 210 | 1050
| News listing + news article detail | Design | 5 | 210 | 1050
| Events listing (grid, list, monthly calendar views) + event detail | Design | 8 | 210 | 1680
| Resource Hub listing + resource detail | Design | 6 | 210 | 1260
| Sponsors / partners section | Design | 4 | 210 | 840
| Additional page templates TBC at Blueprint (est. 3) | Design | 9 | 210 | 1890
Block 3: Core Website Development |  |  |  |  | 10580
| WordPress CMS + GreyboxPro setup + global style engine (brand configuration) | Dev | 10 | 230 | 2300
| Mega menu / navigation build | Dev | 8 | 230 | 1840
| Homepage build | Dev | 10 | 230 | 2300
| Interior / standard page templates (all standard content pages) | Dev | 8 | 230 | 1840
| Contact form (Gravity Forms) | Dev | 3 | 230 | 690
| Site search setup | Dev | 4 | 230 | 920
| Google Analytics 4 + Search Console + reCAPTCHA | Dev | 3 | 230 | 690
Block 4: Custom Development — CPTs & Features |  |  |  |  | 8740
| Events CPT + WordPress calendar plugin + 3 display views (grid, list, monthly) + event detail page | Dev | 18 | 230 | 4140
| Resource Hub CPT (dual taxonomy: Categories + Resource Types) + listing + detail pages — fields defined at Blueprint | Dev | 14 | 230 | 3220
| Sponsor / Ad CPT (existing Mettro component) — adapted + configured for Swimming NSW | Dev | 6 | 230 | 1380
Block 5: Integrations |  |  |  |  | 2500
| Microsoft 365 Forms embedding (nominated pages) | Integration/Tech | 6 | 250 | 1500
| OneDrive document library linking | Integration/Tech | 4 | 250 | 1000
Block 6: Content Entry | Client to supply all content fully written, edited and approved before entry begins. |  |  |  | 4080
| Content entry allowance | Content Entry | 24 | 170 | 4080
Block 7: QA, Golive & Delivery |  |  |  |  | 5340
| Pre-golive QA (browsers, devices, functionality, forms) | QA | 12 | 170 | 2040
| Golive execution + 301 redirects (consolidating 2 existing sites into 1) | QA | 8 | 170 | 1360
| Post-golive QA | QA | 4 | 170 | 680
| CMS training session + handover documentation | PM | 6 | 210 | 1260
|  |  |  | Section subtotal (ex GST) | 48490
|  |  |  | Contingency (10%) | 4849
|  |  |  | Total ex GST | 53339
|  |  |  | GST (10%) | 5333.9
|  |  |  | TOTAL inc GST | 58672.9
OPTIONS
Option A: News Article Migration (Drupal → WordPress) | Mettro has deep experience with Drupal-to-WordPress migrations. 800+ news articles — bulk import exercise. Data mapping, import execution, QA and formatting review. Outside base scope. |  |  |  | 5360
| Data mapping (Drupal fields → WordPress post fields) | Integration/Tech | 8 | 250 | 2000
| Bulk import execution + validation | Integration/Tech | 8 | 250 | 2000
| Post-import QA + formatting review | QA | 8 | 170 | 1360
|  |  |  | Contingency (10%) | 536
|  |  |  | Total ex GST | 5896
|  |  |  | GST (10%) | 589.6
|  |  |  | Option total inc GST | 6485.6
Option B: 12-Month Website Support Plan | TBC — to be discussed with client based on their post-launch support requirements. |  |  |  | TBC
NOTES & ASSUMPTIONS
1. | All prices are estimates only, based on information available at time of writing. Blueprint phase will confirm final scope and any adjustments will be discussed before proceeding.
2. | Design is based on artwork adaptation from client-supplied JPEG files — not original design from scratch. If additional original design work is required beyond adapting provided assets, this will require a revised scope.
3. | Sitemap is assumed to be client-supplied. No sitemap development is included in this estimate.
4. | Content entry allowance assumes client provides all content fully written, edited and approved before entry begins. Entry of images, videos and other media is included within the allocated hours.
5. | Hosting is not included. Client to arrange with their preferred provider. Mettro recommends WP Engine (Australian data centre) — signup link provided at Blueprint stage.
6. | Resource Hub CPT field structure and taxonomy terms to be finalised at Blueprint stage.
7. | Event calendar plugin to be confirmed at Blueprint stage (e.g. The Events Calendar or similar).
8. | M365 integration is embed-only (Microsoft Forms embedded via iframe or widget). No SSO or deep API integration is included.
9. | News article migration (Option A) is outside base scope and can be engaged separately.
10. | Estimate is valid for 30 days from date of issue.