## Estimate
Estimate name
Client | Swimming NSW | Use Type = Header for section headings. |  |  | GST % | 10% |  | Live quote summary
Project | Swimming NSW Website Redevelopment | Header rows show subtotal in price column. |  |  | Contingency % | 10% |  | Labour & materials |  | 630
Prepared by | Mettro | Use Type = Item for inclusions. |  |  | Discount % | 0% |  | Contingency |  | 0
|  | DO NOT delete price and line total fields | [5 empty] | Discount |  | 0
[8 empty] | Subtotal |  | 630
[8 empty] | Total inc GST |  | 693
Type | Scope / inclusion | Price | Role 1 | Hrs | Role 2 | Hrs | Role 3 | Hrs | Material cost | Line total | Section key
Header | Blueprint Strategy | 630 | [8 empty] | Blueprint Strategy
Item | Project setup, brief documents, schedule and client material requests |  | Project Management | 4 | [5 empty] | 630 | Blueprint Strategy
Item | Client and Mettro team kickoff meeting |  | Project Management | 2 | [5 empty] | 0 | Blueprint Strategy
Item | Review of existing Swimming NSW sites, content and asset audit across two sites |  | Strategy | 4 | [5 empty] | 0 | Blueprint Strategy
Item | Content architecture, CPT field definitions, component and template map |  | Strategy | 8 | [5 empty] | 0 | Blueprint Strategy
Item | Blueprint Strategy document |  | Strategy | 3 | [5 empty] | 0 | Blueprint Strategy
Item | Technical framework and plugin recommendations |  | Strategy | 2 | [5 empty] | 0 | Blueprint Strategy
Item | Client sign-off and amendments |  | Project Management | 2 | [5 empty] | 0 | Blueprint Strategy | 2000
Spacer
Header | Design: Artwork Adaptation | 0 | [8 empty] | Design
Item | Homepage design adaptation |  | Design | 10 | [5 empty] | 0 | Design
Item | Mega menu and primary navigation design |  | Design | 3 | [5 empty] | 0 | Design
Item | Interior and standard content page template |  | Design | 5 | [5 empty] | 0 | Design
Item | News listing and news article detail page |  | Design | 5 | [5 empty] | 0 | Design
Item | Events listing (grid, list and monthly calendar views) and event detail page |  | Design | 7 | [5 empty] | 0 | Design
Item | Resource Hub listing and resource detail page |  | Design | 6 | [5 empty] | 0 | Design
Item | Sponsors and partners section |  | Design | 3 | [5 empty] | 0 | Design
Item | Additional page templates (est. 3, confirmed at Blueprint stage) |  | Design | 7 | [5 empty] | 0 | Design
Item | [9 empty] | 0 | Design
Item | [9 empty] | 0 | Design
Spacer
Header | Development | 0 | [8 empty] | Development
Item | WordPress CMS environment setup |  | Development | 2 | [5 empty] | 0 | Development
Item | GreyboxPro theme and global style engine |  | Development | 6 | [5 empty] | 0 | Development
Item | Brand configuration: CSS custom properties, colours and typography |  | Development | 4 | [5 empty] | 0 | Development
Item | Mega menu and primary navigation build |  | Development | 8 | [5 empty] | 0 | Development
Item | Homepage build |  | Development | 10 | [5 empty] | 0 | Development
Item | Interior and standard page template build |  | Development | 6 | [5 empty] | 0 | Development
Item | Contact form (Gravity Forms) |  | Development | 3 | [5 empty] | 0 | Development
Item | Site search configuration |  | Development | 3 | [5 empty] | 0 | Development
Item | Google Analytics 4 and Google Search Console setup |  | Development | 2 | [5 empty] | 0 | Development
Item | reCAPTCHA integration |  | Development | 2 | [5 empty] | 0 | Development
Item | Events Custom Post Type setup |  | Development | 4 | [5 empty] | 0 | Development
Item | WordPress calendar plugin installation and configuration |  | Development | 4 | [5 empty] | 0 | Development
Item | Events grid view and list view |  | Development | 6 | [5 empty] | 0 | Development
Item | Events monthly calendar view |  | Development | 6 | [5 empty] | 0 | Development
Item | Event detail page template |  | Development | 5 | [5 empty] | 0 | Development
Item | Resource Hub CPT setup with dual taxonomy: Categories and Resource Types |  | Development | 5 | [5 empty] | 0 | Development
Item | Resource Hub listing page with filtering |  | Development | 6 | [5 empty] | 0 | Development
Item | Resource Hub detail page template |  | Development | 4 | [5 empty] | 0 | Development
Item | Sponsor and Ad CPT component: adaptation and configuration for Swimming NSW |  | Development | 3 | [5 empty] | 0 | Development
Item | Microsoft 365 Forms: embedding into nominated site pages |  | Integration & Technical | 6 | [5 empty] | 0 | Development
Item | OneDrive document library: linking from relevant pages |  | Integration & Technical | 4 | [5 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Item | [9 empty] | 0 | Development
Spacer
Header | Content and Training | 0 | [8 empty] | Content and Training
Item | Content entry: homepage and interior pages |  | Content Entry | 8 | [5 empty] | 0 | Content and Training
Item | Content entry: news, events and Resource Hub |  | Content Entry | 8 | [5 empty] | 0 | Content and Training
Item | Content entry: sponsors, forms and metadata |  | Content Entry | 4 | [5 empty] | 0 | Content and Training
Item | CMS training session (online or in person) |  | Project Management | 3 | [5 empty] | 0 | Content and Training
Spacer
Header | Golive and Delivery | 0 | [8 empty] | Golive and Delivery
Item | Pre-golive QA: cross-browser and device testing |  | Quality Assurance | 10 | [5 empty] | 0 | Golive and Delivery
Item | Forms, integrations and functionality testing |  | Quality Assurance | 4 | [5 empty] | 0 | Golive and Delivery
Item | 301 redirects: consolidating two existing sites into one |  | Development | 6 | [5 empty] | 0 | Golive and Delivery
Item | Golive execution |  | Quality Assurance | 2 | [5 empty] | 0 | Golive and Delivery
Item | Post-golive QA |  | Quality Assurance | 4 | [5 empty] | 0 | Golive and Delivery
Item | Handover documentation pack |  | Project Management | 2 | [5 empty] | 0 | Golive and Delivery
Item | [9 empty] | 0 | Golive and Delivery
| SUBTOTAL | 630 | [8 empty] | Golive and Delivery
| GST | 63
| TOTAL INC GST | 693
| Approximate annual plugin licensing per year (paid directly by client) | 2000
*Includes Gravity Forms, calendar plugin. WP Engine hosting to be quoted separately. To be confirmed at Blueprint stage.
Optional Add-Ons (ex GST, not included in base estimate above)
| Option A: News Article Migration (800+ articles, Drupal to WordPress): data mapping, bulk import and post-import QA | 5260
| Option B: Standard Content Page Migration (export/import from existing Drupal site) — content audit, import setup, post-migration QA | 2480
All option prices are ex GST. Contingency not applied to optional add-ons.
#REF!
#REF!

## Rates & Settings
Mettro Estimating Guide & Rates
GST % | 10%
Contingency % | 10%
Retainer / commitment discount % | 0%
After-hours multiplier | 2
Role / category | Rate ex GST | Row Types
Strategy | 270 | Header
Project Management | 210 | Item
Design | 210 | Spacer
Development | 230
Integration & Technical | 250
Digital Marketing | 220
Copywriting | 210
Content Entry | 170
SEO/AEO/GEO | 210
Quality Assurance | 170
Standard Support | 200
12-Month Support Plan | 170
External Contractor | 200